## Project tracker
Photography project tracker
One row per project. Click a stage cell and use the dropdown to set Not started, In progress or Done — progress updates automatically. Delete the example row when you start.
Project / property | Client | Shoot date | Services | Quote total | Inquiry | Estimate | Booking | Pre-shoot | Shoot day | Editing | Review and revisions | Payment | Delivery | Follow-up | Progress | Next step / notes
Example — 123 Main St (delete this row) | Example client |  | Photos + drone |  | Done | Done | Done | In progress | Not started | Not started | Not started | Not started | Not started | Not started | 30% | Send prep checklist to the agent
Template by ShootPortal · shootportal.app

## Stage guide
Stage guide
What each stage in the tracker covers. Mark a stage Done when its “done means” line is true.
Stage | Done means | Key tasks
1. Inquiry | You understand the job and have what you need to price it. | • Reply within your stated response time • Confirm location, date and scope • Ask about usage, deadline and budget • Send your questionnaire or intake form • Log the lead and where it came from
2. Estimate | The client has a clear quote with an expiry date. | • Price from your costs and target margin • List deliverables, timeline and add-ons • State deposit, reschedule and usage terms • Set an expiry date on the quote • Follow up if there’s no reply
3. Booking | The date is locked in and confirmed in writing. | • Get the signed quote or agreement • Collect the deposit, if you take one • Add to your calendar with address and access • Send a booking confirmation
4. Pre-shoot | The site, the client and your gear are ready. | • Send the prep checklist to the client • Confirm access, parking and on-site contact • Check the weather (and airspace for drone work) • Charge batteries, format cards, clean lenses • Prepare the shot list
5. Shoot day | Everything on the shot list is captured and backed up. | • Arrive early and walk through the site • Work through the shot list • Capture alternates of key shots • Back up files before you leave • Leave the property as you found it
6. Editing | Final files are exported in every size and format promised. | • Import, back up and cull • Edit to your style guide • Check verticals, color and consistency • Remove or blur sensitive details if needed • Export and name files consistently
7. Review and revisions | The client has approved the final selection. | • Share a proof gallery or review link • Collect feedback in one round • Make the agreed revisions • Quote extra changes separately
8. Payment | The invoice is paid in full. | • Send the invoice with a due date • Apply any deposit already paid • Send a reminder around the due date • Mark paid and send a receipt
9. Delivery | The client has the final files and knows how they may use them. | • Deliver final files by gallery or link • Include a usage and licensing summary • Confirm the client received everything • Archive the project and files
10. Follow-up | The relationship is set up for the next job. | • Send a thank-you • Ask for a review or testimonial • Ask permission to use work in your portfolio • Note what to improve next time • Schedule a check-in for future work
Template by ShootPortal · shootportal.app